## KEY (hidden)
Status
Not Started
In Work
Complete

## PROJECT_PLAN
Today's Date | 2024-06-24 | AWS RE/START PROJECT PLAN
Cohort Start Date | 2022-06-01
Cohort Duration | 12
Cohort End Date | 2022-08-22
Start Countdown | -754
End Countdown | -672
Hidden |  |  |  |  | 1900-01-29
PHASE | REPEATS BY | TASK | DETAILS | STATUS | TARGET DATE
Planning
| - | Secure Funding to Deliver Cohorts | Identify funding to start the first cohort and develop a plan for sustainment funding to continue future cohorts | Not Started | 2022-03-03
| - | Request access for Admin Resources and/or Curriculum | Request access to admin resources and/or curriculum from aws-restart-support@amazon.com | Not Started | 2022-03-03
| - | Review AWS re/Start Program Guide | Walk-through of Program Guide/program overview | Not Started | 2022-03-03
| - | Request Access for S3 Metrics Folder | Request Access for S3 metrics folder for metrics reporting, review metric onboarding guide, Q&A sessions available by request | Not Started | 2022-03-03
| - | Review Marketing Resources in AWS re/Start CO Portal | After reviewing Marketing Resources, agree upon Co-Marketing Guidelines with AWS | Not Started | 2022-03-03
| - | Submit the Marketing Sign-up Link Form for Learner Application Website | Submit the Marketing Sign-up Link Form for review and approval. While creating the website, use the approved co-messaging language for the website (and other external materials - flyers, etc.). See the PR Guidelines for a full list of external materials that go through AWS re/Start marketing review. | Not Started | 2022-03-03
| Year | Agree with AWS on timing and volume of upcoming Cohort Dates | Agree with AWS on timing and volume of upcoming Cohort Dates | Not Started | 2022-03-03
| Year | Sign/Return AWS Work Order | Upon receipt and approval of your cohort dates, AWS will release the work order to commit the number of cohort deliveries, sign and return this document via DocuSign | Not Started | 2022-03-03
| City | For In-Person Delivery, Confirm Audio-Visual Classroom Space | If applicable, secure classroom facility for in classroom delivery in line with AWS re/Start Program Guide requirements | Not Started | 2022-04-02
| City | Secure Computers, Verify Devices and Internet Meet Requirements | Verify computing equipment meets program tech specifications using AWS re/Start Program Guide | Not Started | 2022-04-02
| Cohort | Build Employer Demand and Identify Interview Opportunities | Source interview opportunities for graduates | Not Started | 2022-05-02
| City | Review/Enroll Leaners Against Intake Requirements | Screen learner applications against program intake requirements. Submit support template found in the Support Request Templates document in the AWS re/Start CO Portal | Not Started | 2022-05-02
| Cohort | Submit the Instructor Proposal Form (Foundation) | Submit an Instructor candidate through the Salesforce form before the deadline of 3 weeks before cohorts starts | Not Started | 2022-05-11
Delivery
| Cohort | Fill out the AWS re/Start Delivery Intake Metrics in the AWS re/Start CO Portal | Fill out the AWS re/Start Delivery Metrics Form | Not Started | 2022-06-01
| Cohort | Fill out the AWS re/Start Funding Metrics in the AWS re/Start CO Portal | Fill out the AWS re/Start Funding Metrics Form | Not Started | 2022-06-01
| Cohort | Review AWS re/Start Digital Badge and Graduate Requirement Document (Foundation) | Review AWS re/Start Digital Badge requirements in order to understand graduation validation requirements for learners | Not Started | 2022-06-01
| Cohort | Review AWS Certification Exam Voucher Instructions (Foundation) | Review the AWS Certification Exam gudiance documents for instructions to request exam vouchers for graduates | Not Started | 2022-06-01
| Cohort | Monitor learner progress toward graduation in Canvas (Foundation) | Learners who have met graduation requirements will receive digital badges upon completion of the program. COs should monitor learner progress throughout the program | Not Started | 2022-08-05
Closing
| Cohort | Match Graduates to Roles/Interview Opportunities | Our goal is connect 100% of graduates to an interview opportunity with a large number of those converting to work placements. Please ensure every graduate has at least one interview opportunity | Not Started | 2022-08-21
| - | Request and distribute vouchers to graduates | Each graduate who has been validated in Canvas, based on system criteria, will receive an AWS re/Start digital badge. Each of these graduates may receive up to one discounted voucher, as requested by the CO | Not Started | 2022-08-21
| - | Fill out AWS reStart customer support form with certification outcomes of graduates | Once all graduates report to you their exam outcomes, please share those at the cohort level with AWS re/Start via this form: https://support.aws.amazon.com/#/contacts/aws-restart | Not Started | 2022-08-21
| - | Complete the job placement information for AWS re/Start Graduate | Share the AWS re/Start Graduate job placement details in the Placement tab of the portal. One placement detail for each learner | Not Started | 2022-09-29
| - | Review Staff Contact Information | Access to the Portal and Canvas should be limited to active staff only. Please ensure that your staff and instructors contact information is current. If an Instructor or Staff is no longer with the program, please mark them inactive | Not Started | 2022-09-29
Fill out Cohort Start Date and Cohort Duration (highlighted in yellow) to populate Target Date for each task.

## Legend (hidden)
Duration
8
9
10
11
12
13
14
15
16